# Project Design Status Report

Hardware-Accelerated Grayscale Image Convolution Coprocessor
Group 18 — CS 224, Nexys A7 (Artix-7 XC7A100T)

Group Number: 18

## 1. System Summary (≤ 4 lines)

- A hardware-accelerated 3×3 grayscale convolution coprocessor on Nexys A7 (Artix-7), driven by a custom RV32I + RV32M 3-stage pipeline with DSP48E1-inferred MAC units and a memory-mapped MMIO coprocessor interface.

- Integration stage — Phase 1 (RV32M 8-op extension) complete; Phase 2 coprocessor RTL simulation-verified; full FPGA board-level synthesis pending.

- All 8 RV32M ops pass (33/33); conv engine (33/33) and line buffer (29/29) sim-verified; MMIO decoder integrated; CustomTkinter GUI and C software workloads active.

## 2. Scope Tracking

| Component | Description | Status (Done / Partial / Not Started) | Expected Completion Date | Evidence |
| --- | --- | --- | --- | --- |
| Minimum System | RV32I 3-stage pipeline (IF/ID → EX → WB) with hazard unit: data forwarding, load-use stalls, and branch handling. | Done | Apr 3, 2026 | FPGA (Demo 1) |
|  | RV32M 8-op ALU (MUL, MULH, MULHSU, MULHU, DIV, DIVU, REM, REMU) via rv32m_alu with DSP48E1 inference and 32-cycle iterative divider FSM. | Done | Mar 31, 2026 | Testbench: 33/33 ALU tests |
|  | Pipeline stall: pipe_stall = stall_read ¦¦ div_busy; start gated on ~div_busy to prevent FSM re-trigger; hazard unit exhaustively tested. | Done | Apr 3, 2026 | Design: f1167b9 |
| Goal System | 3×3 conv engine (conv_engine.v) with DSP48E1 MAC array — 9-tap dot product per output pixel. 33/33 tests passed. | Done | Apr 18, 2026 | Testbench: 33/33 conv tests |
|  | Line buffer (line_buffer.v) with pipelined BRAM — synchronous latency resolved via pipeline register insertion. 29/29 tests passed. | Done | Apr 18, 2026 | Testbench: 29/29 LB tests |
|  | MMIO decoder: kernel regs 0x80000000–0x80000020, START at 0x80000024, STATUS at 0x80000028, NORM at 0x80000030, SW_DONE at 0x80000034. | Done | Apr 12, 2026 | Design: 2965104 |
| Stretch Goal | Extended SW kernel library — multiple filter presets (Sobel, Laplacian, sharpen) selectable at runtime via UART command. | Not Started |  |  |
|  | Variable kernel size support (1×1, 3×3, 5×5) switchable in coprocessor without RTL recompilation. | Not Started |  |  |

Note:

- “Done” = working on FPGA; otherwise mark Partial

- Evidence: validation / FPGA result / Design: GIT commit reference

## 3. Design Goals Tracking

- Goals are measurable (see project abstract report)

| Metric | Target | Current | Status (Met / Close / Not Met) |
| --- | --- | --- | --- |
| Latency | ≤ (W×H + 4) cycles for W×H image | TBD (FPGA synthesis not yet run) | Not Met |
| Throughput | 1 pixel/cycle (fully pipelined) | 1 pixel/cycle (sim-verified in tb_conv_engine) | Met |
| Resource Usage: LUT | ≤ 40,000 LUTs | TBD | Not Met |
| Resource Usage: FF | ≤ 40,000 FFs | TBD | Not Met |
| Resource Usage: BRAM | ≤ 8 BRAMs | TBD (2 BRAMs used: img_bram_in, img_bram_out) | Not Met |
| Resource Usage: DSP | ≤ 12 DSP48E1 blocks | TBD (9 MACs in conv_engine + divider in rv32m_alu) | Not Met |
| Correctness | 100% SW reference match (byte-identical output) | 131/131 simulation tests passing | Met (simulation) |

## 4. Demonstration Plan Status

- For Apr 25 - 26 (Final Demo)

| Component | Planned | Current Status (1-2 lines) |
| --- | --- | --- |
| Input | Load 8-bit grayscale BMP via UART → BRAM controller → img_bram_in | Sim-verified; GUI sends image bytes over serial |
| Processing | CPU → MMIO → conv engine → poll STATUS until done | MMIO integrated; sw_gaussian_blur.c runs on pipeline |
| Output | UART TX → GUI display + save to PNG | CustomTkinter GUI ready; output save to PNG implemented |

## 5. Gantt Chart

- Implement and be ready with at least one core functionality by Apr 12.

- Complete the full minimum system by Apr 19, leaving buffer for last-minute surprises.

- For Mar 22 – Apr 12: update based on actual execution

- For after Apr 12: fill as planned schedule

- Sample:

|  |  | March |  |  |  |  |  |  |  |  |  | April |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Owner | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Shaurya | Shaurya |  |  |  |  |  |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |
| Sukhjot | Sukhjot |  |  |  |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |
| Soumik | Soumik |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |  |
| Satish | Satish |  |  |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |
| Abhirup | Abhirup |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |

## 6. Risk Tracking

| Risk | Status (New / Ongoing / Resolved) | Impact (High, Medium) | Owner | Mitigation Plan (1 line) |
| --- | --- | --- | --- | --- |
| DIV multi-cycle handling | Resolved | High | Shaurya | FSM gates start on ~div_busy; re-trigger loop fixed; 33/33 tests pass. |
| Kernel write lockout missing — kernel regs writable while conv engine is mid-run. | Ongoing | Medium | Satish | Gate kernel reg writes on ~conv_busy in mmio_decoder; enforce all 9 writes before asserting START. |
| MMIO address mismatch (doc vs RTL) | New | Low | Satish / Shaurya | Doc lists START=0x80000028; RTL uses 0x80000024. Confirm final addresses before demo. |
| FPGA synthesis not complete | Ongoing | High | Shaurya (integration) | Run Vivado implementation before Apr 25 to get resource report and confirm timing closure. |

7. Per-Person Contribution

| Member | Planned | Status (Done, WIP, Not started) | Estimated Completion Date |
| --- | --- | --- | --- |
| Shaurya | rv32m_alu.v — all 8 RV32M ops with DSP48E1 inference and 32-cycle iterative divider FSM | Done | Apr 5, 2026 |
|  | tb_rv32m_alu.v — stress-test all 8 ops incl. div-by-zero, INT_MIN/−1; 33/33 passing | Done | Apr 5, 2026 |
|  | Integration lead — merge all branches, MMIO fix, wire coprocessor in pipeline.v; demo coordination | WIP | Apr 25, 2026 |
| Sukhjot | hazard_unit.v (fwd + stall) — Done; decoder_ext.v (RV32M decode) — Done; SW support — WIP | Done / WIP | Apr 5 / Apr 19 |
| Soumik | conv_engine.v (33/33 tests), line_buffer.v (29/29 tests), img_bram_in/out.v — Phase 2 RTL | Done | Apr 12, 2026 |
| Satish | mmio_decoder.v — Done; conv_datapath.v — Done; top_fsm.v — WIP | Done / WIP | Apr 16 / Apr 25 |
| Abhirup | UART controller — Done; sw_gaussian_blur.c + Makefile — WIP; CustomTkinter GUI — Done | Done / WIP | Apr 12–19, 2026 |

- For activities marked Done, mention the actual completion date.

- For others, provide the estimated completion date.

- WIP = Work in Progress.

## 8. GitHub Snapshot

- Repo: https://github.com/Sukhjot-SinghS/Image-Convulation-FPGA

| Member | Commits (count) |
| --- | --- |
| Shaurya | 12 |
| Sukhjot | 31 |
| Soumik | 6 |
| Satish | 27 |
| Abhirup | 27 |
| Total | 103 |

Key Commits (with 2-3 line description)

| Commit Title | Description |
| --- | --- |
| b163f42 — Merge Sukhjot’s fixes into shaurya branch | Final integration: imported working RTL from Sukhjot’s branch, resolved 28 file conflicts prioritizing functional fixes, added Windows Makefile compatibility. |
| 8b22e70 — Integrate coprocessor, UART + SW utilities (Clean) | Full Phase 2 integration: fixed line_buffer BRAM latency, wired top_fsm drain, brought in UART controller and C workloads; 131/131 tests passing post-merge. |
| 2965104 — Full MMIO decoder for kernel regfile + status reads | Maps kernel weights to 0x80000000–0x80000020, START to 0x80000024, STATUS to 0x80000028; adds SW_DONE doorbell for software-triggered TX. |
| 87ff069 — Add CustomTkinter GUI for FPGA coprocessor | Premium dark-mode GUI: sends 128×128 image over UART, reads 126×126 convolved output, displays side-by-side comparison, saves convolved PNG to disk. |
| 56357c8 — Add RV32M ALU module | Initial rv32m_alu.v: 8-op RV32M ALU with single-cycle multiply (DSP48E1) and 32-cycle iterative restoring divider FSM. |
| 903e18e — Add sw_sobel + rename to blur (Sukhjot) | Renamed sw_sobel.c → sw_gaussian_blur.c; updated Python GUI to save convolved output as timestamped PNG. |

## 9. Changes Based on TA Inputs

- TA feedback to be added after Apr 25–26 final demo review.

- Changes will be documented post-demo based on TA evaluation.

| Feedback/Input | Original | Current | Change |
| --- | --- | --- | --- |