# Project Design Status Report

Hardware-Accelerated Grayscale Image Convolution Coprocessor
Group 18 — CS 224, Nexys A7 (Artix-7 XC7A100T)

Group Number: 18

## 1. System Summary (≤ 4 lines)

- A hardware-accelerated 3×3 grayscale convolution coprocessor on Nexys A7 (Artix-7), driven by a custom RV32I + RV32M 3-stage pipeline with DSP48E1-inferred MAC units and a memory-mapped MMIO coprocessor interface.

- Integration stage — Phase 1 (RV32M 8-op extension) complete; Phase 2 coprocessor RTL simulation-verified; full FPGA board-level synthesis pending.

- All 8 RV32M ops pass (33/33); conv engine (33/33) and line buffer (29/29) sim-verified; MMIO decoder integrated; CustomTkinter GUI and C software workloads active.

## 2. Scope Tracking

| Component | Description | Status (Done / Partial / Not Started) | Expected Completion Date | Evidence |
| --- | --- | --- | --- | --- |
| Minimum System | RV32I 3-stage pipeline (IF/ID → EX → WB) with hazard unit: data forwarding, load-use stalls, and branch handling. | Done | Apr 5, 2026 | FPGA (Demo 1) |
|  | RV32M 8-op ALU (MUL, MULH, MULHSU, MULHU, DIV, DIVU, REM, REMU) via rv32m_alu with DSP48E1 inference and 32-cycle iterative divider FSM. | Done | Apr 5, 2026 | Testbench: 33/33 ALU tests |
|  | Pipeline stall: pipe_stall = stall_read ¦¦ div_busy; start signal gated on ~div_busy to prevent FSM re-trigger loop. | Done | Apr 5, 2026 | Design: f1167b9 |
| Goal System | 3×3 conv engine (conv_engine.v) with DSP48E1 MAC array — 9-tap dot product per output pixel. 33/33 tests passed. | Done | Apr 12, 2026 | Testbench: 33/33 conv tests |
|  | Line buffer (line_buffer.v) with pipelined BRAM — synchronous latency resolved via pipeline register insertion. 29/29 tests passed. | Done | Apr 12, 2026 | Testbench: 29/29 LB tests |
|  | MMIO decoder: kernel regs 0x80000000–0x80000020, START at 0x80000028, STATUS at 0x8000002C, with DMEM passthrough. | Done | Apr 16, 2026 | Design: 2965104Design: 2965104 |
| Stretch Goal | C software suite (sw_gaussian_blur.c, sw_sobel.c) compiling via Master Makefile targeting the RISC-V toolchain. | DonePartial | Apr 19, 2026 | Active (builds clean) |
|  | CustomTkinter Python GUI (demo.py): sends kernel + image over UART, reads convolved output, displays side-by-side comparison. | Done | Apr 18, 2026 | Design: 87ff069 |

Note:

- “Done” = working on FPGA; otherwise mark Partial

- Evidence: validation / FPGA result / Design: GIT commit reference

## 3. Design Goals Tracking

- Goals are measurable (see project abstract report)

| Metric | Target | Current | Status (Met / Close / Not Met) |
| --- | --- | --- | --- |
| Latency | ≤ (W×H + 4) cycles for W×H image | TBD (pending FPGA synthesis) | Not Met |
| Throughput | 1 pixel/cycle (fully pipelined) | 1 pixel/cycle (sim-verified) | Met |
| Resource Usage: LUT | ≤ 40,000 (≤ 63% of 63,400) | TBD | Not Met |
| Resource Usage: FF | ≤ 40,000 | TBD | Not Met |
| Resource Usage: BRAM | ≤ 8 BRAMs | TBD | Not Met |
| Resource Usage: DSP | ≤ 12 DSP48E1 blocks | TBD | Not Met |
| Correctness | 100% match with SW reference (byte-identical output) | 131/131 simulation tests passing | Met (simulation) |

## 4. Demonstration Plan Status

- For Apr 25 - 26 (Final Demo)

| Component | Planned | Current Status (1-2 lines) |
| --- | --- | --- |
| Input | Load 8-bit grayscale BMP via UART → BRAM controller → img_bram_in | UART-to-BRAM controller sim-verified; Python GUI sends image bytes over serial |
| Processing | CPU writes 3×3 kernel via MMIO (0x80000000), asserts START, polls STATUS | MMIO integrated; sw_gaussian_blur.c compiles and executes on RV32 pipeline |
| Output | Read convolved image from img_bram_out via UART; display in GUI, save to disk | GUI upgraded with customtkinter; output display and save-to-disk ready |

## 5. Gantt Chart

- Implement and be ready with at least one core functionality by Apr 12.

- Complete the full minimum system by Apr 19, leaving buffer for last-minute surprises.

- For Mar 22 – Apr 12: update based on actual execution

- For after Apr 12: fill as planned schedule

- Sample:

|  |  | March |  |  |  |  |  |  |  |  |  | April |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Owner | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| RV32M ALU (rv32m_alu.v) | Shaurya | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Hazard Unit + decoder_ext | Sukhjot | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conv Engine + Line Buffer | Soumik |  |  |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MMIO Decoder + top_fsm | Satish |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |
| UART + C SW + Python GUI | Abhirup |  |  |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ |

## 6. Risk Tracking

| Risk | Status (New / Ongoing / Resolved) | Impact (High, Medium) | Owner | Mitigation Plan (1 line) |
| --- | --- | --- | --- | --- |
| DIV multi-cycle handling | Resolved | High | Shaurya | FSM gates start on ~div_busy; re-trigger loop bug fixed; 33/33 tests pass. |
| Kernel write lockout missing — kernel regs writable while conv engine is mid-run. | Ongoing | Medium | Satish | Gate kernel reg writes on ~conv_busy in mmio_decoder; enforce all 9 writes before asserting START. |
| MMIO address mismatch — doc says START=0x80000028 but RTL (mmio_decoder.v) uses START=0x80000024. | Ongoing | Medium | Satish / Shaurya | Confirm final address map between RTL and C code (hw_conv_mmio.c) before demo. |
| FPGA synthesis and bitstream not yet generated — resource and timing results unknown. | Ongoing | High | Shaurya | Run Vivado implementation before Apr 25; check LUT/FF/BRAM/DSP utilization and timing report. |

7. Per-Person Contribution

| Member | Planned | Status (Done, WIP, Not started) | Estimated Completion Date |
| --- | --- | --- | --- |
| Shaurya | rv32m_alu.v — all 8 RV32M ops, DSP48E1 inference, 32-cycle iterative divider FSM | Done | Apr 5, 2026 |
|  | tb_rv32m_alu.v — stress-test all 8 ops incl. div-by-zero, INT_MIN/−1; 33/33 passing | Done | Apr 5, 2026 |
|  | Integration lead — merge all branches, fix MMIO, wire coprocessor in pipeline.v; demo coordination | WIPWIP | Apr 25, 2026Apr 25, 2026 |
| Sukhjot | hazard_unit.v (fwd + stall) — Done Apr 5; decoder_ext.v (RV32M decode) — Done Apr 5; SW branch consolidation and final RTL fixes — Done Apr 19 | DoneDone / WIP | Apr 5 / Apr 19, 2026Apr 5 / Apr 19 |
| Soumik | conv_engine.v (33/33 tests), line_buffer.v (29/29 tests), img_bram_in/out.v — full Phase 2 RTL | Done | Apr 12, 2026 |
| Satish | mmio_decoder.v — Done Apr 16; conv_datapath.v — Done Apr 16; top_fsm.v — WIP | Done / WIP | Apr 16 / Apr 25, 2026 |
| Abhirup | UART controller — Done Apr 12; sw_gaussian_blur.c + Makefile — WIP; demo.py CustomTkinter GUI — Done Apr 18 | Done / WIP | Apr 12–19, 2026 |

- For activities marked Done, mention the actual completion date.

- For others, provide the estimated completion date.

- WIP = Work in Progress.

## 8. GitHub Snapshot

- Repo: https://github.com/Sukhjot-SinghS/Image-Convulation-FPGA

| Member | Commits (count) |
| --- | --- |
| Shaurya | 12 |
| Sukhjot | 31 |
| Soumik | 6 |
| Satish | 27 |
| Abhirup | 27 |
| Total | 103 |

Key Commits (with 2-3 line description)

| Commit Title | Description |
| --- | --- |
| 8b22e70: Integrate coprocessor, UART + SW utilities (Clean)8b22e70: Integrate coprocessor, UART + SW utilities (Clean) | Full Phase 2 integration: fixed line_buffer BRAM latency via pipeline register insertion, wired top_fsm 4-cycle drain state, brought in UART controller and C workloads; 131/131 simulation tests passing post-merge.Full Phase 2 integration: fixed line_buffer BRAM latency, wired top_fsm drain, brought in UART controller and C workloads; 131/131 tests passing post-merge. |
| 2965104: Implement full MMIO decoder for kernel regfile + status reads2965104: Implement full MMIO decoder for kernel regfile + status reads | Maps kernel weights to 0x80000000–0x80000020 (9 regs), START to 0x80000024, STATUS to 0x80000028, SW_DONE doorbell at 0x80000034, NORM toggle at 0x80000030; adds DMEM passthrough for non-MMIO addresses.Maps 0x80000000–0x80000020 to 9 kernel regs and 0x80000028/0x8000002C to START/STATUS; adds DMEM passthrough for non-MMIO addresses. |
| 87ff069: Add CustomTkinter GUI for FPGA coprocessor interface87ff069: Add CustomTkinter GUI for FPGA coprocessor (demo.py) | Premium dark-mode GUI: sends 128x128 grayscale image over UART, reads 126x126 hardware-convolved result, displays side-by-side comparison and saves output as timestamped PNG. Uses threaded UART worker to avoid GUI freeze.Premium GUI: sends kernel + image over UART, reads convolved output, displays side-by-side comparison with SW reference, saves to disk. |
| b163f42: Merge Sukhjots fixes into shaurya branch | Final integration commit: imported all working RTL from Sukhjots branch; resolved 28 file conflicts prioritizing functional fixes; patched Makefiles for Windows (cp -> copy /Y); system runs end-to-end on shaurya branch. |
| 56357c8: Add RV32M ALU module | Initial rv32m_alu.v commit: implements all 8 RV32M instructions. Multiplies are single-cycle using DSP48E1 inference. Divides use a 32-cycle iterative restoring-division FSM with alu_busy_o stall signal. |

## 9. Changes Based on TA Inputs

- TA feedback to be added after Apr 25–26 final demo review.

- Changes will be documented post-demo based on TA evaluation.

| Feedback/Input | Original | Current | Change |
| --- | --- | --- | --- |