# Project Design Status Report

Title
Hardware-Accelerated Grayscale Image Convolution Coprocessor on Artix-7

Group 18

## 1. System Summary (≤ 4 lines)

- 3-stage RV32I + RV32M pipeline CPU extended with a memory-mapped 3x3 grayscale convolution coprocessor targeting the Nexys A7 (Artix-7 XC7A100T).

- Partial implementation — Phase 1 (RV32M CPU) synthesized and FPGA-verified; Phase 2 (coprocessor) integrated in top-level, all submodule testbenches passing (131/131).

- RV32M ALU (all 8 ops, DSP-inferred, 29/29 tests pass); conv_engine, line_buffer, img_bram verified; mmio_decoder and kernel_regfile wired to pipeline.

## 2. Scope Tracking

| Component | Description | Status (Done / Partial / Not Started) | Expected Completion Date | Evidence |
| --- | --- | --- | --- | --- |
| Minimum System | RV32I + RV32M pipeline CPU (all 8 MUL/DIV/REM ops) | DONE | 31 MAR 2026 | tb_rv32m_alu: 29/29 PASS. Pipeline on FPGA. Commit: 56357c8 |
|  | 5 C workloads running on CPU via software toolchain | PARTIAL | 16 APR 2026 | Testbenches running, FPGA integration pending. Commit: 7bdb482 |
|  | Hazard unit + data forwarding for RAW hazards | DONE | 31 MAR 2026 | Commit: 85d9807 |
| Goal System | Hardware convolution coprocessor via MMIO | PARTIAL | 18 APR 2026 | conv files + mmio_decoder.v integrated in top-level |
|  | Programmable 3x3 kernel register file | PARTIAL | 18 APR 2026 | kernel_regfile.v written and wired to MMIO |
|  | SW vs HW timing comparison | NOT STARTED | 20 APR 2026 | Requires fully verified hardware pipeline |
| Stretch Goal | Triple-Channel RGB Processing | NOT STARTED | 24 APR 2026 | Depends on baseline Goal System completion |
|  | Interactive Kernel Switching | NOT STARTED | 24 APR 2026 | Requires working Python GUI to FPGA pipeline |

Note:

- &#x201C;Done&#x201D; = working on FPGA; otherwise mark Partial

- Evidence: validation / FPGA result / Design: GIT commit reference

## 3. Design Goals Tracking

- Goals are measurable (see project abstract report)

| Metric | Target | Current | Status (Met / Close / Not Met) |
| --- | --- | --- | --- |
| Latency | >50x reduction for 64x64 image vs SW | FPGA integration in progress | Not Met (Pending Benchmarks) |
| Throughput | 0.25 output pixel / clock cycle | Submodule simulation complete | Close |
| Resource Usage: LUT | < 63,400 | ~5,000 - 8,000 | Close |
| Resource Usage: FF | < 126,800 | ~4,000 - 6,000 | Close |
| Resource Usage: BRAM | < 135 | 4 to 6 blocks | Close |
| Resource Usage: DSP | < 240 | 11 (9 MAC + 2 MUL) | Close |
| Correctness | 100% Golden Ref match | Submodules verified (131/131 tests) | Close |

## 4. Demonstration Plan Status

- For Apr 14 (Mini Demo)

| Component | Planned | Current Status (1-2 lines) |
| --- | --- | --- |
| Input | RV32M test program loaded via IMEM hex file | Hex loaded; tb_rv32m_alu running. DONE |
| Processing | 3-stage RV32IM pipeline execution with M-extension | All 8 RV32M ops verified; DIV stalls up to 32 cycles. DONE |
| Output | Register file dump via GTKWave waveform | tb_rv32m_alu self-checks, reports PASS/FAIL. DONE |

- For Apr 25 - 26 (Final Demo)

| Component | Planned | Current Status (1-2 lines) |
| --- | --- | --- |
| Input | 128x128 grayscale image + 3x3 kernel via UART from Python host | image_transfer.py ready; UART RX/TX integrated. PARTIAL |
| Processing | HW convolution via MMIO; CPU writes kernel, polls STATUS | conv_engine, line_buffer, top_fsm verified; MMIO integrated. PARTIAL |
| Output | Blurred/sharpened output image displayed in Python GUI | Blurred output image + timing data via Python GUI. NOT STARTED |

## 5. Gantt Chart

- Implement and be ready with at least one core functionality by Apr 12.

- Complete the full minimum system by Apr 19, leaving buffer for last-minute surprises.

- For Mar 22 – Apr 12: update based on actual execution

- For after Apr 12: fill as planned schedule

- Sample:

|  |  | March |  |  |  |  |  |  |  |  |  | April |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Owner | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| RV32I Pipeline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RV32M ALU + Hazard Unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MMIO + Kernel Regfile |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conv Engine + Line Buffer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| …. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## 6. Risk Tracking

| Risk | Status (New / Ongoing / Resolved) | Impact (High, Medium) | Owner | Mitigation Plan (1 line) |
| --- | --- | --- | --- | --- |
| DIV multi-cycle handling | Resolved | High | Shaurya | start gated by ~div_busy in execute.v; FSM re-trigger loop eliminated |
| MMIO integration bugs: kernel write lockout missing; START race before all 9 kernel words committed | Ongoing | Medium | Satish | kernel write lockout gating on ~conv_busy; STATUS latch verified in sim |

7. Per-Person Contribution

| Member | Planned | Status (Done, WIP, Not started) | Estimated Completion Date |
| --- | --- | --- | --- |
| Shaurya | rv32m_alu.v: all 8 MUL/DIV/REM ops, DSP-inferred, 32-cycle iterative divider FSM | Done | 31 MAR 2026 |
|  | Python GUI (demo.py): image send/receive pipeline over serial | WIP | 20 APR 2026 |
|  | tb_rv32m_alu.v: stress testbench 29/29 PASS (all edge cases incl. div-by-zero, INT_MIN/-1) | Done | 31 MAR 2026 |
| Sukhjot | hazard_unit.v: forwarding logic + stall control for RV32I/M pipeline | Done | 31 MAR 2026 |
|  | decoder_ext.v: RV32M instruction decode (funct3/funct7 decode) | Done | 31 MAR 2026 |
|  | Integration testing: pipeline hazard smoke tests with tb_pipeline.v | Done | 05 APR 2026 |
| Satish | mmio_decoder.v: MMIO address decode for kernel regs, START/STATUS registers | Done | 05 APR 2026 |
|  | conv_datapath.v + top_fsm.v: convolution datapath and top-level control FSM | WIP | 18 APR 2026 |
|  | Top-level wiring: connecting coprocessor to pipeline in top_fpga.v | WIP | 18 APR 2026 |
| Abhirup | 5 C workloads: matrix multiply, sort, Fibonacci, etc. compiled for RV32IM | Partial | 16 APR 2026 |
|  | UART driver: RX/TX integration for image transfer protocol | Partial | 18 APR 2026 |
| Soumik | conv_engine.v + line_buffer.v: 3x3 sliding window MAC engine | Done | 05 APR 2026 |
|  | img_bram_in.v + img_bram_out.v: dual-port BRAM for image I/O | Done | 05 APR 2026 |
|  | Testbenches for conv_engine and line_buffer | Done | 05 APR 2026 |

- For activities marked Done, mention the actual completion date.

- For others, provide the estimated completion date.

- WIP = Work in Progress.

## 8. GitHub Snapshot

- https://github.com/Sukhjot-SinghS/Image-Convulation-FPGA

| Member | Commits (count) |
| --- | --- |
| Shaurya | 7 |
| Sukhjot | 19 |
| Satish | 27 |
| Abhirup | 21 |
| Soumik | 16 |
| Total | 90 |

Key Commits (with 2-3 line description)

| Commit Title | Description |
| --- | --- |
| 56357c8 | Add rv32m_alu: all 8 RV32M ops, DSP-inferred MUL, 32-cycle iterative DIV FSM |
| 85d9807 | Add hazard_unit + decoder_ext for RV32M data forwarding and stall logic |

## 9. Changes Based on TA Inputs

- What feedback was received in the project presentation

- What changes were made

| Feedback/Input | Original | Current | Change |
| --- | --- | --- | --- |